## Sheet1
geth - node.js communicaiton: june | -
github: src code/ wiki | all | [13 empty] | Semi-final |  | Final
| By | 2017-11-30 | 2017-12-01 | 2017-12-02 | 2017-12-03 | 2017-12-04 | 2017-12-05 | 2017-12-06 | 2017-12-07 | 2017-12-08 | 2017-12-09 | 2017-12-10 | 2017-12-11 | 2017-12-12 | 2017-12-13 | 2017-12-14 | 2017-12-15
setup private chain: charles | charles | 2017-11-30: the chain is workable now; 2017-12-12: 3 days
deploy smart contract: charles | charles | 2017-11-30: assume no big change any more; 2017-12-12: 1 day
ppt & hsbc communication | Angie | bar: 2017-12-07 to 2017-12-12
write smart contract: june/charles | charles | 2017-11-30: assume no big change any more
screen design and dev: June | june | bar: 2017-11-30 to 2017-12-10
node.js call smart contract: june | june/refly | bar: 2017-12-05 to 2017-12-11
smart contract event handling (node.js): june | june/refly | bar: 2017-12-05 to 2017-12-11
atmp | refly | 2017-11-30: assume no big change any more
atmc | refly | bar: 2017-11-30 to 2017-12-11
server setup: terence (main): | terence | 2017-11-30: done
connectivity test |  | 2017-12-02: done
customer journey
demonstrate transaction flow and data flow | June | bar: 2017-12-05 to 2017-12-11
Nice to have items: | Priority
retrieve customer transaction record from ATMP? | 3
retrieve transaction record from blockchain? | 4
data encryption? | 2
Operation? E.g. how to clear totals between banks | 1